## Bradford
Strategy or Action | Description | Responsibility | Timing (Ongoing, short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Parking lot and trailhead development | Build a parking lot on Highway 25 with a trailhead and work with the landowner for purchase. | Town/ Conservation Commission | Long-Term | Private landowners | Parking lot and trail design | $$$$ | LWCF, RTP, RTC, RFG, TCPN
Winter access | Have the town road crew plow the Chase Hollow Road and trailhead in the winter to ease pressure on Wright's Mountain Road and provide a more diverse experience. | Town | Short-Term | Conservation Commission | -- | $$ | --
School bus access | Modify existing parking lots or construct new parking lot to accommodate school buses. | Conservation Commission | Medium-Term | Town | Parking lot design | $$ | LWCF, RTP, TAP
New trailheads | Place new trailhead signs at Devil's Den and Tillotson's Trek to alleviate confusion. | Conservation Commission | Short-Term | -- | Kiosk design | $ | RTP, RTC, VCF, AIG
Vehicle wayfinding signage | Add and improve vehicle wayfinding signage from town and major roadways to the forest. Place signage on Route 25 and near the intersection of Corner Fairground Road and Route 5. | Town/ Conservation Commission | Short-Term | UVLT | Signage Design | $$ | BPP, Vtrans Signage Program
2. Trails
Existing trail conditions assessment and review | Study existing trails, especially those following former logging roads, and evaluate for potential ecological harm and mitigate the site through necessary means. Decommission or reroute trails as needed. | Conservation Commission | Short-Term | UVTA, UVMBA, other trail builders | Trail reroute and redesign | $$ | RTP, RTC, VHCP, ERG
New mountain bike trails | If forest is expanded, build "bike-optimized" multi-use natural surface trails to expand recreational offerings and encourage new visitation to town and forest. Otherwise, consider rebuild or replacement of existing multi-use trails. | Conservation Commission | Long-term | UVTA, UVMBA, other trail builders | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New ADA accessible path | If forest is expanded, build a graded, ADA accessible path for all ages and abilities to enjoy the forest.. Such paths are typically short (~1 mile) and provide ample opportunities for rest and education with stations or stops next to points of natural or cultural interest. Coordinate with educational programming. | Conservation Commission | Long-term | UVTA, other trail builders | Trail design | $$$ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New educational boardwalk/wetland overlook | Build a short boardwalk or wetland overlook to provide educational opportunities about vernal pools and/or wetlands. Limit length of boardwalk and encroachment into wetland to minimum necessary for educational/interpretive needs. | Conservation Commission | Medium-term | Four Winds, program and educational partners | Boardwalk/viewing pier design | $$ | LWCF, RTC, RTP, RFG, AIG
3. Other Amenities and Facilities
Pause Places | Develop a series of "Pause Places" or "mini-destinations' along the trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, sunsets, rest, and rejuvenation. Opportunities for natural and historical interpretation should also be explored. Some could also include public art or a 'little free library.' Focus efforts on Wright's MT side which has fewer currently. | Conservation Commission | Medium-Term | Program and educational partners | History and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Create and maintain locations for birding and viewing wildlife. | Build more locations to sit and observe wildlife. Benches are encouraged in a variety of locations. Coordinate with Pause Places. Devil's Den is an ideal location for this. | Conservation Commission | Medium-Term | Program and educational partners | History and natural resource research, pause place design | $ | LWCF, RTC, RTP, RFG, AIG
Cabin Improvement | Explore opportunities to improve the cabin to better support day use, educational use, and potentially overnight use. Explore potential relationship with Vermont Huts Association. | Conservation Commission | Medium-Term | Programming and educational partners, Vermont Huts Association | Potentially architectural, depending on level of improvement | $$$-$$$$ | LWCF, RTC, RTP, RFG, AIG
4. Education & Programs
Adult-centered activities/programs | Offer activities and programs in the forest geared towards adults such as bird watching or adult hikes and bike rides. | Conservation Commission | Short-Term | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Kids camps | Continue to host kids camps in the forest by partnering with Bradford Parks and Recreation, churches and others operating camps in the area. | Conservation Commission | Short-Term | Bradford Parks and Recreation Department, Four Winds, program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Lessons, skills camps, and clinics | Offer lessons, skills camps, and clinics for trail running. | Bradford Parks and Recreation Department | Short-Term | Conservation Commission | -- | $ | VCF, VHCB, LF, BJF
Ecology tours | Offer ecology tours (birdwatching, plant identification, etc.) for children and adults. | Conservation Commission | Short-Term | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Timber management education | Create awareness and education programs around the timber management of the forest. | Conservation Commission | Medium-Term | County Forester, UVLT | -- | $ | CCG, ERG
Interpretive signage | Develop interpretive signage that support educational programs and self-guided learning. Coordinate with development of the pause places and limit to avoid cluttering the forest. | Conservation Commission | Short-Term | Program and educational partners | History and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Species identification lists | Bird, plant and mammal species identification checklists could be developed and made available at the trailhead kiosk and vernal pools. Should also be utilized in education experiences. | Conservation Commission | Short-Term | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Story Walk | A StoryWalk is an innovative and delightful way for children — and adults! — to enjoy reading and the outdoors at the same time. Laminated pages from a children's book are attached to wooden stakes, which are installed along an outdoor path. As you stroll down the trail, you're directed to the next page in the story. | Conservation Commission | Medium-Term | Library, Program and educational partners | -- | $$ | VCF
5. Events
Regularly scheduled events | The Conservation Commission, in collaboration with Parks and Recreation, should host regularly scheduled events in the forest and post the events on the town calendar or other public calendar sites. | Conservation Commission | Ongoing | Parks and Recreation Department, program and educational partners, Town | -- | $ | VCF, LF, BJF
6. Maps, Outreach, & Promotion
Online presence | Improve the online presence of the forest with a forest specific website. Work with Chamber of Commerce to coordinate activities and continue working with Upper Valley Trails Alliance (UVTA) to promote the forest. | Conservation Commission | Short-Term | UVTA, UVLT, Town, Cohase Chamber of Commerce | Website design | $-$$ | RTP, VCF
Publicize events | Post forest events on town calendar and public calendar sites such as the Cohase Chamber of Commerce. | Conservation Commission | Short-Term | UVTA, UVLT, Town, Cohase Chamber of Commerce | Website design | $ | RTP, VCF
Improve and better utilize maps of the forest | Make the forest maps readily available both online and in print. Explore opportunities to engage local businesses in sponsoring map printing. Ads from local businesses can not only fund map printing, but can also help connect forest use with economic activity in the village. Add designated camping areas, outhouses, and snowmobile trails to future maps. | Conservation Commission | Medium-Term | UVTA, UVLT, UVMBA, Cohase Chamber of Commerce | Cartography, Graphic Design | $-$$ | RTP
Town Forest Business Roundtable | Host a Town Forest Business Roundtable to share "trail friendly business" ideas that can help support trail use in the community, connect forest visitors with local businesses, and help support Town Forest efforts. | Conservation Commission | Medium-Term | Town, Cohase Chamber of Commerce, local businesses | -- | $ | VCF
Hunter Engagement | Convene hunters to begin an on-going dialogue around hunting activities and to. establish a framework for collaboration and coordination in the future. | Conservation Commission | Medium-Term | Local hunters, residents | Meeting facilitation | $ | NPCB
7. Administrative Actions
Connection to Newbury Town Forest | Explore recommissioning of Stagecoach Road as a trail connection with Newbury Town Forest. | Conservation Commission | Long-Term | Town, Town of Newbury, Newbury Conservation Commission, landowners | ROW research, trail plan/design | $$ | BCP, BPP, STBG, TAP, MPG, RTP, RTC
Economic Impact Study | Conduct economic impact study to determine the economic benefit the forest provides the town to gather resident support for the forest. | Conservation Commission | Short-Term | Town, Cohase Chamber of Commerce | Trail counting, economic impact assessment | $$ | MPG, BCP
Expand Town Forest | Explore opportunities to expand the Town Forest with adjacent landowners, particularly at the top of Wright's Mountain. | Conservation Commission | Long-Term | Town, UVLT, VLT | Due diligence and land planning | $$$-$$$$ | LWCF, RD, VHCP
Bradford Trails Collaborative | Develop a consistent volunteer force for trail maintenance and programs with members from Upper Valley Mountain Bike Association, UVTA, UVLT, and other trail groups. | Conservation Commission | Short-Term | UVTA, UVMBA, trail users | Meeting facilitation | $ | NPCB
Adopt formal process for proposing and reviewing new trails and facilities | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. | Conservation Commission | Short-Term | UVTA, UVMBA, trail users | Review, adjustment and adoption of model process | $ | RTP, RTC, VHCP, ERG
Management zones | Make public aware of existing management zones and continue to include in future management plans. | Conservation Commission | Long-Term | -- | Management Plan Update | $ | --
Partner with Bradford Parks and Recreation | Partner with Bradford Parks and Recreation to utilize the Town Forest for Town recreation programs and to benefit from staff expertise. | Conservation Commission | Short-Term | Bradford Parks and Recreation Department | -- | $ | --
Partner with Little Rivers Health Care | Partner with Little Rivers Health Care to promote healthy lifestyles through recreation in the Town Forest. | Conservation Commission | Short-Term | Bradford Parks and Recreation Department | -- | $ | --

## Hardwick
Strategy or Action | Description | Responsibility | Timing (Ongoing, short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Improve access to Buffalo Mountain | Explore new locations on Buffalo Mountain for parking and public access. Consider parking opportunities from Kate Brook Road/Buffalo Mountain Road. | Town/ Town Forest Committee | Medium-Term | Trails Committee, VAST-Ridge runners, other users | Road, Parking lot and trailhead design | $$$$ | LWCF, RD, RFG
Trail network connectivity | Explore options for linking both Buffalo Mountain and Hazen Union to surrounding trail networks and rail networks (i.e. Hardwick to Woodbury Rail Trail, Lamoille Valley Rail Trail, Highland Lodge trails, and Craftsbury trails). | Trails Committee | Medium-Term | LVRT, Woodbury, Craftsbury, Town/ Town Forest Committee, etc. | Trails Master Plan, individual designs | $$$ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
Vehicle wayfinding signage | Add vehicle wayfinding signage from town and major roadways to Buffalo Mountain. | Town/ Town Forest Committee | Medium-Term | Vtrans/Town Highway Department | Signage design | $$ | BPP, Vtrans Signage Program
Encourage linking trail networks to town center | Encourage the connectivity of trail networks with the town center and create an in-town access point and parking where trail users can depart or return to | Town/ Town Forest Committee | Medium-Term | Trails Committee, etc. | Trails Master Plan | $$ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
2. Trails
Existing trail conditions assessment and review | Study current trail infrastructure on Buffalo Mountain and Hardwick Trails to asses baseline of current trails and logging roads to establish direction in future trail development and design. Decommission trails or reroute trails as needed. | Trails Committee | Short-Term | -- | Trail reroute & redesign | $ | RTP, RTC, VHCP, ERG
New trails at Hardwick Trails | Add loop trail north of Billings Road. Add connection trails to Lamoille Valley Rail Trail and to Craftsbury Outdoor Center. | Trails Committee | Medium-Term | Craftsbury, VAST-Ridge runners, LVRT | Trail design | $$$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
Trail spur to the Lamoille Valley Rail Trail | Build a short spur trail to connect the Hardwick Trails with the Lamoille Valley Rail Trail, possibly as an ADA accessible path. | Trails Committee | Medium-Term | LVRT, VAST-Ridge runners | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New rugged multi-use paths on Buffalo Mountain | Develop multi-use non-motorized natural surface trails that are optimized for hiking and foot traffic but designed to accommodate multiple user groups. | Trails Committee | Medium-Term | -- | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New mountain bike trails on Buffalo Mountain | Build "bike-optimized" multi-use natural surface trails to ensure desired experiences for all user groups. | Trails Committee | Medium-Term | -- | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New snowmobile and ATV trails on Buffalo Mountain | Develop additional motorized use trails on Buffalo Mountain. Consider further improvements to Wright Farm Road. | VAST-Ridge runners | Medium-Term | Trails Committee | Trail design | $$$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
Ensure sustainable trail building | Ensure that ecologically sensitive areas are protected from degradation by looking to the Sustainable Trail Standards and Natural Resource Guidance Toolkit. | Trails Committee | Ongoing | All | -- | $ | --
Multi-season trail use with a variety of activities | Forest activities in all seasons are currently in action and should continue into the future. While some trails may need to be rerouted or reconstructed to better accommodate desired uses, the current layout of the Hardwick Trails seems to be working well. Four season trail use is encouraged into the future. | Trails Committee | Ongoing | -- | Trail reroute & redesign | $ | RTP, RTC, VHCP, ERG
Continue to support groomed winter trails | The groomed cross-country ski trails have been identified as a fabulous community resource, but the effort puts a strain on the town's dedicated trail volunteers. More resources and equipment would help support the long-term sustainability of the grooming program. | Trails Committee | Ongoing | -- | -- | $$$$ | RTP, LF, BJF
3. Other Facilities and Structures
Update and expand public rental equipment at Hardwick Trails | Seek funding sources to purchase more cross-country ski, mountain biking, snow showing, etc. equipment which can be made publicly available for rent | Trails Committee | Short-Term | -- | -- | $$ | VCDP, VCF, LF, BJF, TCPN
Build a warming hut on Buffalo Mountain | Building a rest area/warming hut at near summit of Buffalo Mountain is of interest. Structures such as this may be year-round facilities to serve trail users in all seasons. Consider a lean-to or open sided pavilion as part of the structure. | Town/ Town Forest Committee | Medium-Term | Trails Committee, VAST-Ridge runners, other users | Architecture and design | $$$$ | LWCF, RD, VCDP, RFG, VCF, LF, AIG, BJF
Pause Places | Develop a series of "Pause Places" or "mini-destinations' along the Buffalo Mountain trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, sunsets, rest, and rejuvenation. The summit of Buffalo mountain has been identified as a potential location of interest given the views. Opportunities for natural and historical interpretation should also be explored. Some could also include public art. | Trails Committee | Long-Term | Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Create and maintain locations for birding and viewing wildlife. | Build more locations to sit and observe wildlife at Hardwick Trails and new locations at Buffalo Mountain.. Benches are encouraged in a variety of locations. Coordinate with Pause Places. | Trails Committee | Long-Term | Program and educational partners | Pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
4. Education & Programs
Existing programming in the forest should continue | Continue existing education, camp, and art programs in the forest. Engage programs about needs in development of any new trail connections, interpretive signage, or pause places. | Town/ Town Forest Committee | Ongoing | Program and educational partners | Pause place design | $ | --
Coordinate nature education, photography, nature writing and other classes | Where community members are utilizing the town forest for public nature education classes, ensure that a town forest class schedule is made publicly available | Town/ Town Forest Committee | Short-Term | Program and educational partners | -- | $ | TCPN
Maintain opportunities for GMTCC Forestry program | The GMTCC Forestry Program relies on the town forest for forestry education, professional development and programmatic diversity and the forest should be made available to the program in the future. | Town/ Town Forest Committee | Ongoing | GMTCC | -- | $ | --
Botany and plant identification | Create plant and tree identification tags that can be placed around the forest where they are visible to hikers and can educate the public on dendrology and the silvics of the forest. Integrate species lists with this effort accordingly. | Town/ Town Forest Committee | Medium-Term | Program and educational partners | -- | $$ | RTP, RTC
Interpretive signage | Develop interpretive signage that supports educational programs and self-guided learning. Coordinate with development of the pause places | Town/ Town Forest Committee | Short-Term | Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Story Walk | A Story Walk is an innovative and delightful way for children — and adults! — to enjoy reading and the outdoors at the same time. Laminated pages from a children's book are attached to wooden stakes, which are installed along an outdoor path. As you stroll down the trail, you're directed to the next page in the story. | Trails Committee | Medium-Term | Library | -- | $ | VCF
5. Events
Races in the forest | Hold small-scale mountain bike, trail running or Nordic races in the forest. Consider race series or local-serving adventure race (GMARA or Tough Mudder, etc.) as well. . | Trails Committee | Medium-Term | Race organizers, etc. | Event and parking plan | $ | VCF, VHCB, LF, BJF
6. Maps, Outreach, & Promotion
Improve maps for both Town Forests | Create maps that show all trails in the forest and make these maps readily available both online and in print. Explore opportunities to engage local businesses in sponsoring map printing. Ads from local businesses can not only fund map printing, but can also help connect forest use with economic activity in the village. | Trails Committee | Medium-Term | Town/ Town Forest Committee | Graphic design | $-$$ | RTP
Update the Hardwick Trails website | Update the Hardwick Trails website to ensure content is current and fresh, particularly around the Buffalo Mountain parcel; | Trails Committee | Medium-Term | Town/ Town Forest Committee | Website design | $ | TCPN
Mapping Buffalo Mountain | Map development of the Buffalo Mountain parcel is encouraged and there is a need to establish baseline environmental conditions with field surveys and detailed analysis. | Town/ Town Forest Committee | Short-Term | Trails Committee | Mapping and natural resource inventory | $$ | CCG, MPG, ERG, VCF, VHCP, BJF
Measure forest use | Use trail counters or volunteer trail counts to gather data about the number of users of the Hardwick Trails. | Trails Committee | Short-Term | Town/ Town Forest Committee | -- | $/$$ | RTP, RTC, Regional Planning Commission
7. Administrative Actions
Adopt formal process for proposing and reviewing new trails and facilities | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. | Town/ Town Forest Committee | Medium-Term | Trails Committee | Review, adjustment and adoption of model process | $ | --
Create Town Forest Committee | Where the management focus extends beyond trail maintenance, consider utilizing a Committee that represents a variety of perspectives from the community. Such a committee should include at least one representative from the Hazen Union School, GMTCC, the Trails Committee, the Town of Hardwick, and other public members as deemed necessary by the community. | Town | Short-Term | Trails Committee | -- | $ | --
Coordinate maple syrup production with recreational trail use | Where seasonal recreational use of Hardwick Trails conflicts with the infrastructure and use of the forest for Maple Syrup production, seek to coordinate uses and minimize conflict through collaborative management. | Trails Committee | Ongoing | GMTCC | -- | $ | --
Create a Management Plan for the Buffalo Mountain Town Forest | Plan for the long-term success of the forest through developing a forest management plan. Coordinate with the management zones in the forest. | Town/ Town Forest Committee | Medium-Term | Trails Committee | -- | $$ | CCG, MPG, ERG, VCF, VHCP, BJF
Create a Management Plan for Hazen Union | Plan for the long-term success of the forest through developing a forest management plan. Coordinate with the management zones in the forest. Maintaining aesthetics and stewardship of natural features/resources should be included as components of any management plan. | Town/ Town Forest Committee | Medium-Term | Trails Committee | -- | $$ | CCG, MPG, ERG, VCF, VHCP, BJF
Management zones | Consider management zones of the forest to consider and plan for all uses. Designate areas more suitable for wildlife habitat, hunting, or mountain biking, for example. | Town/ Town Forest Committee | Medium-Term | -- | -- | $ | CCG, MPG, ERG, VCF, VHCP, BJF

## Hartford
Strategy or Action | Description | Responsibility | Timing (Ongoing, short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Vehicle wayfinding signage | Add vehicle wayfinding signage from villages to the forest. | Town Forest Steering Committee/ Conservation Commission | Short-Term | Vtrans/Town Highway Department | Signage design | $$ | BPP, Vtrans Signage Program
2. Trails
Existing trail conditions assessment and redesign | The Hartford Town Forest has both sanctioned and unsanctioned trails with sustainability issues. Therefore, undergoing a review of the existing trails and redesigning the system based on the results of the review has been a top priority. | Town Forest Steering Committee/ Conservation Commission | Ongoing | UVTA, UVMBA, local builder/users | Trail reroute & redesign | $$$ | RTP, RTC, VHCP, ERG
Hartford Trails Collaborative | Convene mountain bikers, hikers, and other user groups to begin an ongoing dialogue around trails and to establish a framework for collaboration in the future. Build upon partnerships with Upper Valley Trail Alliance (UVTA). | UVTA and Town Forest Steering Committee/ Conservation Commission | Short-Term | UVMBA, GMC, UVLT, etc. | Meeting facilitation | $ | RTP, NPCB
Trail markers and signage | Add signage in the forest for wayfinding, information, and trail etiquette. Ensure it communicates town ownership and/or conservation commission management. | Town Forest Steering Committee/ Conservation Commission | Short-Term | UVTA, UVMBA, local builder/users | Signage and wayfinding plan | $$ | RTP, RTC
3. Other Facilities and Structures
Pause Places | Develop a series of "Pause Places" or "mini-destinations' along the trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, sunsets, rest, and rejuvenation. Opportunities for natural and historical interpretation should also be explored. Some could also include public art or a 'little free library.' | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Create and maintain locations for birding and viewing wildlife. | Build more locations to sit and observe wildlife. Benches are encouraged in a variety of locations. Coordinate with Pause Places. Caution should be taken to not changing the character of the forest. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
4. Education & Programs
Develop a trail maintenance program | Work with Hartford Career & Tech Center on a trail maintenance program. School groups or Boy Scouts are other possible maintenance groups. Coordinate with trails collaborative effort. Seek participation from all five villages. | UVTA and Town Forest Steering Committee/ Conservation Commission | Short-Term | UVMBA, GMC, UVLT, etc. | Meeting facilitation | $ | RTP, NPCB
Host school group programs in the forest | Bring students to the forest for ecology programs, recreation programs, etc. Consider a high school mountain biking team. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Ecology tours | Offer ecology tours (birdwatching, plant identification, etc.) for children and adults. | Program and educational partners | Medium-Term | Town Forest Steering Committee/ Conservation Commission | -- | $ | VCF, VHCB, LF, BJF
Lessons, skills camps, and clinics | Offer lessons, skills camps, and clinics for trail running and mountain biking. | Program and educational partners | Medium-Term | Town Forest Steering Committee/ Conservation Commission | -- | $ | VCF, VHCB, LF, BJF
Species identification lists | Bird, plant and mammal species identification checklists could be developed and made available at the trailhead kiosk. Should also be utilized in education experiences. | Town Forest Steering Committee/ Conservation Commission | Short-Term | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Story Walk | A StoryWalk is an innovative and delightful way for children — and adults! — to enjoy reading and the outdoors at the same time. Laminated pages from a children's book are attached to wooden stakes, which are installed along an outdoor path. As you stroll down the trail, you're directed to the next page in the story. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Library | -- | $ | VCF
5. Events
Races in the forest | Hold small-scale, local mountain bike, trail running, or nordic skiing races in the forest. | Program and event partners | Medium-Term | Town Forest Steering Committee/ Conservation Commission | Event and parking plan | $ | VCF, VHCB, LF, BJF
6. Maps, Outreach, & Promotion
Improve maps of the forest | Create maps that show all trails in the forest and make these maps readily available both online and in print. Explore opportunities to engage local businesses in sponsoring map printing. Ads from local businesses can not only fund map printing, but can also help connect forest use with economic activity in the villages. Ensure it communicates town ownership and/or conservation commission management. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | UVTA, Trails Collaborative | Graphic design | $-$$ | RTP
Online presence | Improve the online presence of the forest with a forest specific website. Work with Chamber of Commerce to coordinate activities and continue working with Upper Valley Trails Alliance (UVTA) to promote the forest. Ensure it communicates town ownership and/or conservation commission management. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | UVTA, Chamber of Commerce | Website design | $-$$ | RTP, VCF
Town Forest Business Roundtable | Host a Town Forest Business Roundtable to share "trail friendly business" ideas that can help support trail use in the community, connect forest visitors with local businesses, and help support Town Forest efforts. | Town Forest Steering Committee/ Conservation Commission | Long-term | Local business, Chamber of Commerce | -- | $ | VCF
7. Administrative Actions
Adopt formal process for proposing and reviewing new trails and facilities | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. | Town Forest Steering Committee/ Conservation Commission | Short-Term | Hartford Trails Collaborative | Review, adjustment and adoption of model process | $ | --
Management zones | Revise management zones of the management plan to consider and plan for all uses. Designate areas more suitable for wildlife habitat, hunting, or mountain biking, for example. | Town Forest Steering Committee/ Conservation Commission | Long-term | UVLT | Update to Management Plan | $ | --
Partner with Hartford Parks and Recreation | Partner with Hartford Parks and Recreation to utilize the Town Forest for Town recreation programs and to benefit from staff expertise. | Town Forest Steering Committee/ Conservation Commission | Short-Term | Hartford Parks and Recreation | -- | $ | --

## Hinesburg
Strategy or Action | Description | Responsibility | Timing (On-going, Short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Parking lot and trailhead development | Develop parking lots along Economou Road. |  |  |  |  | $$$
Improve resiliency of access points | Improving road conditions including the class 4 portion of the Hayden Hill road is encouraged. |  |  |  |  | $$$
Vehicle wayfinding signage | Add/improve vehicle wayfinding signage from town and major roadways to the forests. |  |  |  |  | $$
2. Trails
Existing trail conditions assessment and review | Study current trail infrastructure to assess baseline of current trails to establish the direction in future trail development and design. Decommission, rebuild, or reroute trails as needed. Updating drainage on the Eagles Trail has been encouraged. |  |  |  |  | $
New rugged multi-use paths | Develop multi-use non-motorized natural surface trails that are optimized for hiking and foot traffic but designed to accommodate multiple user groups Consider rebuild or replacement of existing multi-use trails. |  |  |  |  | $$
New mountain bike trails | Build "bike-optimized" multi-use natural surface trails to enure desired expereinces for all user groups Consider rebuild or replacement of existing multi-use trails. |  |  |  |  | $$
Plan for winter use of the trail systems | Accommodate snowshoeing, cross-country skiing and fat-biking in the forest. Consider groomed winter trails as a possible option. |  |  |  |  | $$
Supporting dog Walking | Dog walking in the forest has been expressed as a high priority. Consider providing signage for dog walkers at the trail head. |  |  |  |  | $$
New backcountry/glade skiing opportunities | Explore opportunities for expanding backcountry/glade skiing in combination with sustainable forest management activities. |  |  |  |  | $$
Hunting in the forest | Continue to accommodate hunting in the forest. Many have expressed interest in using the parcel for hunting and thus signage alerting other hikers of the importance in wearing blaze orange and leashing/marking their dogs during the hunting season is encouraged. |  |  |  |  | $
3. Other Facilities and Structures
Pause Places | Develop a series of "Pause Places" or "mini-destinations' along the trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, sunsets, rest, and rejuvenation.. Opportunities for natural and historical interpretation should also be explored. Some could also include public art or a 'little free library.' |  |  |  |  | $$
Plan for lookout/scenic vista points | XX and XX locations have been sugested and appear to provide excellent view opporunities. Review suggested locations and integrate into trail system and pause place plan. |  |  |  |  | $$
Develop a restroom at the Trailhead | Provide restroom facilities, privy, or composting toilet at the trailhead.. |  |  |  |  | $$$
4. Education & Programs
Exisitng programming in the forest should continue | Continue existing education, camp, and art programs in the forest. Engage programs about needs in development of any new trail connections, interpretive signage, or pause places. |  |  |  |  | $
Coordinate nature education, photography, nature writing and other classes | Where community members are utilizing the town forest for public nature education classes, ensure that a town forest class schedule is made publicly available |  |  |  |  | $
Ecology tours | Offer ecology tours (birdwatching, plant identification, etc.) for children and adults. |  |  |  |  | $
Kids camps | Offer kids camps in the forest. Partner with Hinesburg Parks and Recreation, churches and others operating camps in the area. |  |  |  |  | $
Continued Maple syrup Production | Maintain the active sugar-bush and promote sugaring in the forest. Aim to coordinate with the trails in place and recreational pursuits. |  |  |  |  | $
Interpretive signage | Develop interpretive signage that support educational programs and self-guided learning. Coordinate with development of the pause places |  |  |  |  | $$
Species identification lists | Bird, plant and mammal species identification checklists could be developed and made available at the trailhead kiosk. Should also be utilized in education experiences. |  |  |  |  | $
Story Walk | A StoryWalk is an innovative and delightful way for children — and adults! — to enjoy reading and the outdoors at the same time. Laminated pages from a children's book are attached to wooden stakes, which are installed along an outdoor path. As you stroll down the trail, you're directed to the next page in the story. |  |  |  |  | $$
5. Events
Races in the forest | Hold mountain bike or trail running races in the forest. Consider race series or local-serving adventure race (Tough Mudder, Warrior Dash, etc.) as well. . |  |  |  |  | $
6. Maps, Outreach, & Promotion
Community Engagement | Continue to engage the entire community about the forest to make it feel like a shared resource. |  |  |  |  | $
Measure forest use | Use trail counters or volunteer trail counts to gather data about the number of users of the Hazen-Union Forest. |  |  |  |  | $/$$
Updated maps of the forest | Create maps that show all trails in the forest and make these maps readily available both online and in print. Explore opportunities to engage local businesses in sponsoring map printing. Ads from local businesses can not only fund map printing, but can also help connect forest use with economic activity in the villages. |  |  |  |  | $-$$
Town Forest Business Roundtable | Host a Town Forest Business Roundtable to share "trail friendly business" ideas that can help support trail use in the community, connect forest visitors with local businesses, and help support Town Forest efforts. |  |  |  |  | $
Building a coalition of volunteers | Have a group of volunteers on hand for activities such as trail maintenance, events or other needs of the forest. Look to engage the Hinesburg Land Trust, VMBA, Iroquois Snow Beavers Snowmobile club, Hinesburg Area Recreational Trails committee, Fellowship of the Wheel, and Vermont Land Trust.
7. Administrative Actions
Continue to work with the Fellowship of the Wheel (FOTW) | Continued partnership with the FOTW is encouraged as the biking trail system has benefited from their work in, and commitment to the forest.
Adopt formal process for proposing and reviewing new trails and facilities | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. |  |  |  |  | $
Partner with Hinesburg Parks and Recreation | Partner with Hinesburg Parks and Recreation to utlize the Town Forest for Town recreation programs and to benefit from staff expertise. |  |  |  |  | $

## Huntington
Strategy or Action | Description | Responsibility | Timing (Ongoing, short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Acquire a new town forest | Identify and move forward with the purchase of a new town forest in Huntington that will provide more opportunities for access, recreation, and education. Retain the current Town Forest property for conservation. | Town/Conservation Commission | Medium-Term | Land Conservation Partners (Vermont Land Trust, Trust for Public Land, etc.) | Due diligence and land planning | $$$$ | LWCF, RD, VHCP
Build and maintain parking access | Build and maintain parking access for current and future public land and recreation | Town/Conservation Commission | Long-Term | FPR, Camel's Hump Nordic Ski Area | Parking lot design | $$$ | LWCF, RD, RFG
Partner with state parks, forest, and nearby towns | Partner with state parks, forest, and nearby towns to provide accessible forest-based outdoor recreation opportunities for Huntington residents. | Town/Conservation Commission | Short-Term | Vermont Department of Forests, Parks, and Recreation; Hinesburg; Richmond; Bolton | -- | $ | --
State Forest and Park Access | Work with Camel's Hump State Forest & Park to improve access to recreational opportunities on their land. | Town/Conservation Commission | Short-Term | Camel's Hump State Forest and Park | -- | $ | --
Access paths and connections | Develop access path between town trails and town center. | Town | Medium/Long-Term | All | Trails Master Plan | $$$ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
Vehicle wayfinding signage | Add vehicle wayfinding signage from town to the trails and recreation areas. | Town/Conservation Commission | Medium/Long-Term | -- | -- | $$ | BPP, Vtrans Signage Program
2. Trails
Existing trail conditions assessment and review | Study the trails and logging roads that currently exist in town and consider needs for future trail building. | Town/Conservation Commission | Short-Term | FPR, Camel's Hump Nordic Ski Area, Snow Beavers, other trail managers | Part of Trails Master Plan | $ | BCP, MPG
New rugged multi-use paths | Develop multi-use non-motorized natural surface trails that are optimized for hiking and foot traffic but designed to accommodate multiple user groups | Town/Conservation Commission | Medium/Long-Term | VYCC, other trail builders | Trails Master Plan | $$-$$$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New mountain bike trails | Build "bike-optimized" multi-use natural surface trails to ensure desired experiences for all user groups | Town/Conservation Commission | Medium/Long-Term | VYCC, Fellowship of the Wheel, other trail builders | Trails Master Plan | $$-$$$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New ADA accessible path | Develop a graded, ADA accessible path to connect the villages of Huntington. Such paths are typically provide ample opportunities for rest and education with stations or stops next to points of natural or cultural interest. Coordinate with educational programming. | Town/Conservation Commission | Medium/Long-Term | VYCC, other trail builders | Trails Master Plan | $$$-$$$$ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
Trails Master Plan | Develop a Recreational Trails Master Plan to define the what, where, and how for all the trail related strategies listed. | Town/Conservation Commission | Short-Term | All | Part of Trails Master Plan | $$ | BCP, MPG
Private land trails | Explore opportunities for partnerships with private owners to increase trail access | Town/Conservation Commission | Short-Term | All | Part of Trails Master Plan | $$ | BCP, MPG
Groom trails for cross-country skiing and fat biking | Groom wider trails for public cross-country skiing, fat biking, and snowmobiling.. | Town/Conservation Commission | Short-Term | Camel's Hump Nordic Ski Area, Sleepy Hollow, Snow Beavers | -- | $$ | RTP, VCF
Trail markers and signage (wayfinding) | Develop a robust wayfinding signage system to make the system accessible. | Huntington Trails Collaborative | Medium/Long-Term | All | Trails Master Plan | $$ | RTP
New backcountry/glade skiing opportunities | Explore opportunities for expanding backcountry/glade skiing in combination with sustainable forest management activities. | Town/Conservation Commission | Medium/Long-Term | FPR, Camel's Hump Nordic Ski Area, VT Huts | -- | $$ | RTP, LF
Huntington Trails Collaborative | Convene mountain bikers, hikers, snowmobiliers and other user groups to begin an ongoing dialogue around trails and to establish a framework for collaboration in the future. | Town/Conservation Commission | Short-Term | Fellowship of the Wheel, FPR, Snow Beavers, others | Meeting facilitation | $ | RTP, NPCB
Trail connections | Create connections between existing trails to develop a connected, accessible network of trails in the town | Town/Conservation Commission | Medium/Long-Term | Fellowship of the Wheel, FPR, Snow Beavers, others | Trails Master Plan | $$$ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
3. Other Facilities and Structures
Pause Places | Develop a series of "Pause Places" along the town trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, wildlife observation, sunsets, rest, and rejuvenation. Opportunities for natural and historical interpretation should also be explored. Larger ones may include a picnic table. Some could also include public art or a 'little free library.' | Town/Conservation Commission | Medium-Term | Birds of VT Museum, VT Audubon, FPR, Snow Beavers | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Utilize existing town-owned parcels | Disperse new recreational facilities (outdoor classroom, natural playground, dog park, etc.) amongst existing town-owned recreation parcels if possible. | Town | Medium-Term | Recreation committee | -- | $ | LWCF, RD, RFG
Outdoor Classroom/Learning Lab | Partner with the school to better utilize the outdoor classroom for community use and educational opportunities. | Town/Conservation Commission | Short-Term | Brewster-Pierce Memorial School | -- | $ | --
Natural Playground | Explore opportunities to develop a natural playground in town. Natural playgrounds are play environments that blend natural materials, features, and indigenous vegetation with creative landforms to challenge and fascinate children and teach them about the wonders of the natural world. | Town | Medium/Long-Term | Recreation committee | -- | $$ | LWCF, RD, RFG
Designate areas for off leash trails for dogs and their owners | Explore locations to develop areas to provide a more "wild" off-leash trail experience for dogs and their owners. | Town/Conservation Commission | Short-Term | All | Part of Trails Master Plan | $$$ | --
Sledding | Designate a slope for a sledding hill | Town | Medium/Long-Term | Recreation committee | -- | $ | LWCF, RD, RFG
Ice Skating | Created a protected and accessible opportunity for ice skating at Gillett Pond. Work with Richmond on access to the pond. | Town | Medium/Long-Term | Recreation committee, Richmond, Friends of Gillet Pond | -- | $ | LWCF, RD, RFG
Swimming Hole | Consider conserving a swimming hole on Cobb Brook and creating access. | Town | Medium/Long-Term | Camel's Hump State Forest | -- | $ | LWCF, RD, RFG
Fitness Trail | Build a fitness trail in an existing park or forest in Huntington. Fitness trails are paths with stations set up for physical fitness training. | Town | Medium/Long-Term | Recreation committee | -- | $$ | LWCF, RD, RFG
Art | Design and construct natural art pieces for parks, open spaces, and forests, in the area. Encourage artistic activities in forest and outdoor recreation areas such as natural painting and fairy houses. | Town | Medium/Long-Term | Huntington Valley Arts, Vermont Arts Council, Recreation committee | -- | $ | AIG, VCF
River access | Create river access points for paddle/watersports, swimming, and fishing in the Huntington River. | Town | Medium/Long-Term | Recreation committee | -- | $$ | LWCF, RD, RFG
4. Education & Programs
Partnerships with local schools | Hold field trips about forest ecology and local history at nearby forest areas. Consider use by these groups in new acquisitions or partnership opportunities. | Town/Conservation Commission | Short-Term | Brewster-Pierce Memorial School, Mount Mansfield | -- | $ | --
Partnerships with state/local groups, camps, etc. | Hold kids camps, retreats, or educational activities at nearby forest areas. Consider use by these groups in new acquisitions or partnership opportunities. | Town/Conservation Commission | Short-Term | VT Audubon, Birds of VT Museum | -- | $ | --
Lessons, Skills Camps, and Clinics | Hold lessons, skills camps, and clinics at area trails on mountain biking, trail running, or orienteering. Consider use by these groups in new acquisitions or partnership opportunities. | Town/Conservation Commission | Short-Term | VT Audubon, Birds of VT Museum | -- | $ | --
Health and Wellness | Hold health and wellness programming (i.e., yoga, fitness) at parks, trails, and open space in town. Consider use by these groups in new acquisitions or partnership opportunities. | Town/Conservation Commission | Short-Term | Recreation committee | -- | $ | --
Adult Ecology Programs | Hold adult ecology programs (i.e., birding, plant identification, mycology) at forested areas in town. | Town/Conservation Commission | Short-Term | VT Audubon, Birds of VT Museum | -- | $ | --
Interpretive signage | Develop interpretive signage that support educational programs and self-guided learning. Coordinate with development of pause places. | Town/Conservation Commission | Medium/Long-Term | VT Audubon, Birds of VT Museum | Historical and natural resource research | $$ | LWCF, RTP, RTC, CCG
Species identification lists | Bird, plant and mammal species identification checklists could be developed and made available at trailhead kiosks in town. Should also be utilized in education experiences. | Town/Conservation Commission | Medium-Term | VT Audubon, Birds of VT Museum | -- | $ | VCF, VHCB, LF, BJF
Story Walk | A StoryWalk is an innovative and delightful way for children — and adults! — to enjoy reading and the outdoors at the same time. Laminated pages from a children's book are attached to wooden stakes, which are installed along an outdoor path. As you stroll down the trail, you're directed to the next page in the story. | Town/Conservation Commission | Medium-Term | Huntington Public Library | -- | $ | VCF
5. Events
Races in the town | Hold small-scale mountain bike or trail running races in the town. Consider race series or local-serving adventure race (Tough Mudder, Warrior Dash, etc.) as well. Consider potential for such events in new acquisitions or partnership opportunities. | Green Mountain Adventure Racing, Fellowship of the Wheel | Medium-Term | Town/Conservation Commission | Event and parking plan | $ | VCF, VHCB, LF, BJF
Host community events | Host community events at existing parks and open spaces in town. Consider potential for such events in new acquisitions or partnership opportunities. Examples include cider festivals, haunted forest walk, or winter carnivals. | Town/Conservation Commission | Medium-Term | Recreation committee | Event and parking plan | $ | --
6. Maps, Outreach, & Promotion
Develop and disseminate trail maps | Create maps that show all trails in the town and make these maps readily available both online and in print. Explore opportunities to engage local businesses in sponsoring map printing (businesses in neighboring towns too!). Ads from local businesses can not only fund map printing, but can also help connect forest use with economic activity in the region. | Town/Conservation Commission | Medium-Term | Fellowship of the Wheel, FPR, Snow Beavers, others | Graphic Design | $-$$ | RTP
Assessment of current recreational opportunities | Assess and map current recreational opportunities in Huntington. | Town/Conservation Commission | Short-Term | All | Part of Trails Master Plan | $$ | BCP, MPG
Outdoor Recreation Business Roundtable | Host an Outdoor Recreation Business Roundtable to share "trail friendly business" ideas that can help support trail use in the community, connect forest visitors with local businesses, and help support Town Forest efforts. | Town/Conservation Commission | Long-Term | Local business, Chamber of Commerce | -- | $ | VCF
7. Administrative Actions
Adopt formal process for proposing and reviewing new trails and facilities | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. | Town/Conservation Commission | Short-Term | Huntington Trails Collaborative | Review, adjustment and adoption of model process | $ | --
8. Stewardship
Remove invasives | Remove invasive plants that are growing in the forest. | Town/Conservation Commission | Short-Term | -- | -- | $ | LF, VHCP, BJF
Continue stewardship activities on existing town forest | Update the 2009 Management Plan to ensure that current activities are maximizing habitat conservation and incorporate best practices and strategies. | Town/Conservation Commission | Ongoing | -- | -- | $$ | CCG, MPG, ERG, VCF, VHCP, BJF
Conserve natural areas | Conserve existing natural areas in town as designated open space. Seek conservation easements that provide for public recreational access if possible | Town/Conservation Commission | Medium-Term | Land Conservation Partners (Vermont Land Trust, Trust for Public Land, etc.) | Due diligence and land planning | $$ | CCG, MPG, ERG, VCF, VHCP, BJF

## Marshfield
Strategy or Action | Description | Responsibility | Timing (Ongoing, short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Jake Martin Road Access | Complete the Jake Martin Road Access project by constructing a trail from the parking area to the Moonfield to avoid the private property by the forest. Maps should also be posted at the trailhead kiosk. | Stewardship Committee | Ongoing | RIPM, local trail builders | trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
2. Trails
Existing trail conditions assessment and review | Continue to study existing trails, especially those following former logging roads, and evaluate for potential ecological harm and mitigate the site through necessary means. Decommission or reroute trails as needed. | Stewardship Committee | Short-Term | RIPM, Conservation Commission, local trail builders and users | trail reroute and redesign | $ | RTP, RTC, VHCP, ERG
New Trail Connections | Improve the existing trail system with strategic connections to enhance experiences for all user groups. Ensure system includes a mix of traditional footpaths and "bike-optimized" multi-use natural surface trails to provide desired experiences. Consider rebuild or replacement of existing logging roads or unsustainable trails to improve drainage, limit erosion, and limit trail density. New connections could include an apple picking trail (that leads to the orchard) or connections for an interpretive history trail. | Stewardship Committee | Medium-Term | RIPM, Conservation Commission, local trail builders and users | trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New accessible path or interpretive trail | Build a graded, ADA accessible path for all ages and abilities to enjoy the forest. Such paths are typically short (~1 mile) and provide ample opportunities for rest and education with stations or stops next to points of natural or cultural interest. Coordinate with educational programming. | Stewardship Committee | Long-Term | Local trail builders | trail design | $$$ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
Trail markers and signage | Continue to add signage in the forest for wayfinding, information, and trail etiquette. Ensure it communicates town ownership and/or stewardship committee management. | Stewardship Committee | Short-Term | Conservation Commission, RIPM | Signage design | $$ | RTP, RTC
Marshfield Trails Collaborative | Continue to convene mountain bikers, hikers, and other user groups to begin an ongoing dialogue around trails and to establish a framework for collaboration in the future. | Stewardship Committee | Short-Term | RIPM, VAST | Meeting facilitaiton | $ | RTP, NPCB
3. Other Facilities and Structures
Pause Places | Develop a series of "Pause Places" or "mini-destinations" along the trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, sunsets, wildlife observation, rest, and rejuvenation. Opportunities for natural and historical interpretation should also be explored. | Stewardship Committee | Medium-Term | Program and educational partners | historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Restore Apple Orchard | Restore trail to apple orchard to open up access. Improve the orchard itself to become a community resource. | Stewardship Committee | Medium-Term | -- | -- | $$ | LWCF, RTC, RTP, LF, VCF, BJF
Develop an outdoor classroom | Create a small gathering space with picnic tables, benches, earthen mounds etc. for schools and other groups. | Stewardship Committee | Medium-Term | Earthwalk, Twinfield School | outdoor classroom design | $$ | LWCF, RTC, RTP, RFG, AIG
4. Education & Programs
Educational Programs/Outdoor Program | Continue holding educational programs in the forest about the history and ecology of the forest. | Stewardship Committee | Ongoing | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Ecology tours | Continue offering ecology tours (birdwatching, plant identification, etc.) for children and adults. | Stewardship Committee | Ongoing | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Land management education | Create awareness and education programs around the land management of the forest. Consider interpretive signage. | Stewardship Committee | Medium-Term | County Forester, VLT, Program and educational partners | -- | $ | CCG, ERG. VCF, VHCP, BJF
Interpretive signage | Develop interpretive signage that support educational programs and self-guided learning. Coordinate with development of pause places. | Stewardship Committee | Medium-Term | Program and educational partners | historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Species identification lists | Bird, plant and mammal species identification checklists could be developed and made available at the trailhead kiosk. Should also be utilized in education experiences. | Stewardship Committee | Short-Term | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
5. Events
6. Maps, Outreach, & Promotion
Community Engagement | Continue to engage the community about the forest. Identify community members who have a useful skill to offer. | Stewardship Committee | Ongoing | All | -- | $ | --
Measure forest use | Use trail counters or volunteer trail counts to gather data about the number of users of the forest. | Stewardship Committee | Short-Term | RIPM | -- | $/$$ | RTP, RTC
Improve maps of the forest | Create maps that show all trails in the forest and make these maps readily available both online and in print. Add QR codes to the maps. | Stewardship Committee | Medium-Term | RIPM, Conservation Commission | Cartography, Graphic Design | $-$$ | RTP
7. Administrative Actions
Management zones | Expand use of management zones in town forest management plan to consider and plan for all uses. Designate areas more suitable for wildlife habitat, hunting, or mountain biking, for example. | Stewardship Committee | Long-Term | Town, Conservation Commission, VLT | -- | $ | CCG, MPG, ERG. VCF, VHCP, BJF
Partner with local groups interested in recreation, conservation, and programming. | Partner with the Conservation Commission, Twinfield School, and other local conservation and recreation groups such as VAST, Riders in Plainfield Marshfield (RIPM), and Friends of the Winooski. | Stewardship Committee | Short-Term | All | Meeting facilitaiton | $ | RTP, NPCB
Adopt formal process for proposing and reviewing new trails and facilities | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. | Stewardship Committee | Short-Term | Town, Conservation Commission, VLT | Review, adjustment, and adoption of model process | $ | RTP, RTC, VHCP, ERG
8. Stewardship
Remove invasives | Remove invasive plants that are growing in the forest. | Stewardship Committee | Medium-Term | Conservation Commission | -- | $ | LF, VHCP, BJF

## Middlebury
Strategy or Action | Description | Responsibility | Timing (Ongoing, short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Parking lot and trailhead development | Develop parking lot(s) with trailhead kiosks for Chipman Hill. One parking lot should be large enough to accommodate a school bus. Consider access to Wright Park via Exchange Street. | Town | Long-term | MALT, Trustees, Middlebury College | Parking lot design | $$$ | LWCF, RTP, TAP
Access paths and connections | Develop access paths and bike/ped connections between town forest and downtown. Consider connection from TAM or pedestrian route along Route 7. Focus on connections to schools, hospital, and recreation center. | Town | Medium-term/Long-term | MALT, Trustees, Middlebury College | Active Transportation Master Plan | $$$ | BCP, BPP
Wayfinding signage | Add pedestrian wayfinding signage from downtown and adjacent neighborhoods to the forests. | Town | Short-term | MALT, Trustees, Middlebury College | Signage design | $$ | BPP, Vtrans Signage Program
2. Trails
Existing trail conditions assessment and review | Study existing trails, especially unsanctioned trails, and evaluate for potential ecological harm and mitigate the site through necessary means. Decommission or reroute trails as needed. | Town & Trustees | Short-term | MALT, Middlebury College, ABC, Local builders/ users | Trail reroute & redesign | $ | RTP, RTC, VHCP, ERG
Trail maintenance | Fallen trees have been identified in Battell Woods and those on trails should be removed for accessibility. Dead wood should be left in the woods for ecological and hydrological benefit. | Town & Trustees | Short-term | MALT, Middlebury College, ABC | -- | $ | RTP
Address unsanctioned trails | Close unsanctioned trails in ecologically sensitive areas and adopt some trails. Perform trail maintenance on the newly sanctioned trail and consider turning a few trails into bike-optimized trails. | Town & Trustees | Medium-term | MALT, Middlebury College, ABC | Trail reroute & redesign | $ | RTP, RTC, VHCP, ERG
Safety and Signage in high risk areas | Add wayfinding signage and study the need for crosswalks, warning signs, etc. where trail intersects major roadways (i.e., Route 7). Study a potential underpass at Route 7 crossing. | Town | Long-term | MALT, Trustees, Middlebury College | Signage design, scoping study | $$-$$$$ | BCP, BPP, Vtrans Signage Program
Trail markers and signage | Add signage in the forest for wayfinding, information, and trail etiquette. Ensure it communicates town ownership and/or trust management. Some trails are well marked, while others are not. Seek unified trail markers and signage design. | Town & Trustees | Medium-term | MALT, Middlebury College, ABC | Signage design | $$ | RTP, RTC
Plan for winter use of the trail systems | Accommodate snowshoeing, cross-country skiing and fat biking in the forest. Consider groomed winter trails as a possible option. | Town & Trustees | Short-term | MALT, Middlebury College, ABC | -- | $$ | RTP
3. Other Facilities and Structures
Pause Places | Develop a series of "Pause Places" along the trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, sunsets, rest, and rejuvenation. Opportunities for natural and historical interpretation should also be explored. Larger ones may include a picnic table. Some could also include public art or a 'little free library.' | Town & Trustees | Medium-Term | Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Create and maintain locations for birding and viewing wildlife. | Designate a few pause places for birding and wildlife viewing with appropriate interpretive signage and benches. | Town & Trustees | Medium-Term | Program and educational partners | Natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Repair old bridges and build new ones in wet areas | The west side of Means Woods has bridges which have been identified as in need of repair. Other areas in the forest may benefit from bridge construction also as they are seasonably very wet. | Town & Trustees | Short-term | MALT, Middlebury College, ABC | Bridge design | $$ | RTP, RTC
4. Education & Programs
Interpretive signage | Develop interpretive signage that support educational programs and self-guided learning. Coordinate with development of the pause places. For example, a sign about Joseph Battell in Battell Woods and the land use history of the location. | Town & Trustees | Medium-term | Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Coordinate nature education, photography, nature writing and other classes | Where community members are utilizing the town forest for public nature education classes, ensure that a town forest class schedule is made publicly available | Town & Trustees | Short-term | Program and educational partners | -- | $ | --
Assess current forest programming | Talk to groups currently offering programming in the forest (Hogback Community College, Spirit in Nature, Otter Creek Audubon Society, etc.) about the demand for forest programming. Assess and plan future programming based on this information. | Town & Trustees | Short-term | Program and educational partners | -- | $ | --
Kids camps | Offer kids camps in the forest. Partner with Middlebury Parks and Recreation, churches and others operating camps in the area. | Town & Trustees | Medium-term | Middlebury Parks and Recreation, others | -- | $ | --
Ecology tours | Offer ecology tours (birdwatching, plant identification, etc.) for children and adults. | Program and educational partners | Medium-term | Town & Trustees | -- | $ | VCF, VHCB, LF, BJF
Birding, nature, and wildlife classes | Offer nature classes for the public such as a birding class or scat and track identification lesson. Coordinate these lessons on the trails website and the bird and plant species list. | Program and educational partners | Medium-term | Town & Trustees | -- | $ | VCF, VHCB, LF, BJF
Species identification lists | Bird, plant and mammal species identification checklists could be developed and made available at the trailhead kiosk. Should also be utilized in education experiences. Consider online or smartphone app version. | Town & Trustees | Short-term | Program and educational partners, Audubon Addison County | -- | $ | VCF, VHCB, LF, BJF
Story Walk | A StoryWalk is an innovative and delightful way for children — and adults! — to enjoy reading and the outdoors at the same time. Laminated pages from a children's book are attached to wooden stakes, which are installed along an outdoor path. As you stroll down the trail, you're directed to the next page in the story. | Town & Trustees | Medium-term | Library | -- | $$ | VCF
5. Events
Races in the forest | Continue to hold small-scale race events such as the TAM Trek in the forests. Consider other running, XC skiing, or mountain biking races or local-serving adventure race (Tough Mudder, Warrior Dash, etc.) in the forests. | Program and Event Partners | Short-term | Town & Trustees | Event and parking plan | $ | VCF, VHCB, LF, BJF
7. Administrative Actions
Formalize Organizational and Decision-Making Structure | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. | Town & Trustees | Short-term | MALT, Middlebury College, ABC, Conservation Commission, etc. | Review, adjustment and adoption of model process | $ | RTP, RTC, VHCP, ERG
Work with Middlebury Area Land Trust | As MALT has worked closely with the town in managing the forest and the TAM, engage MALT on future projects to ensure that any alterations to the TAM abide by the terms of the easement and requirements of MALT. | Town & Trustees | Short-term | MALT | -- | $ | --
Habitat Mapping and Inventory | Conduct detailed habitat surveys to guide future management of the forest. | Town & Trustees | Medium-term | Middlebury College | -- | $$ | CCG, MPG, ERG, VCF, VHCP, BJF
Create a Management Plan for each of the Town Forest parcels. | Plan for the long term success of the forest through developing a forest management plan which can be coordinated with the management zones in the each of the forest parcels. Plan for the continued connectivity of the forested region. The 2000-10 Middlebury Comprehensive Parks and Rec. Plan calls for management plans of Battell Woods and Chipman Hill specifically. | Town & Trustees | Long-term | MALT, Middlebury College, ABC | -- | $ | CCG, MPG, ERG, VCF, VHCP, BJF
Management zones | Consider management zones of the forest to consider and plan for all uses. Designate areas more suitable for wildlife habitat, hiking, or mountain biking, for example. | Town & Trustees | Long-term | MALT, Middlebury College, ABC | -- | $ | CCG, MPG, ERG, VCF, VHCP, BJF
Water Quality | Conduct a detailed water quality and hydrology analysis to guide future management of the forest. | Town & Trustees | Long-term | MALT, Middlebury College, ABC | -- | $ | CCG, MPG, ERG, VCF, VHCP, BJF
Partner with Middlebury Parks and Recreation | Partner with Middlebury Parks and Recreation to utilize the Town Forests for Town recreation programs and to benefit from staff expertise. | Town & Trustees | Short-term | Middlebury Parks and Recreation | -- | $ | --

## Richmond
Strategy or Action | Description | Responsibility | Timing (Ongoing, short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Parking lot and trailhead development | Develop parking lot(s) along Route 2 with trailhead kiosks. One parking lot should be large enough to accommodate a school bus. | Town/Steering Committee | Short-Term | VLT, Conservation Commission | Parking lot design | $$$ | LWCF, RTP, TAP
Access paths and connections | Develop access path between town forest and town center. Consider connection from River trail or pedestrian route along Route 2. | Town | Medium-Term | Steering Committee, Richmond Trails | Trail design | $$$ | BCP, BPP
Vehicle wayfinding signage | Add vehicle wayfinding signage from town and major roadways to the forest. | Town | Medium-Term | Steering Committee | Signage design | $$ | BPP, Vtrans Signage Program
2. Trails
Existing trail conditions assessment and review | Study the trails and logging roads that currently exist on the property and consider potential for future trail building. Existing corridors may provide opportunities, but should be rebuilt to sustainable trail standards for both user experience and natural resource protection. | Steering Committee, Richmond Trails | Short-Term | Richmond Mountain Trails, VYCC, local builders/users, Conservation Commission | Trail reroute and redesign | $ | RTP, RTC, VHCP, ERG
Trail network connectivity | Design trail network to connect to adjacent trail systems such as VYCC and Sip of Sunshine. | Steering Committee, Richmond Trails | Medium-Term | Private landowners | Trail design | $ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New rugged multi-use paths | Develop multi-use non-motorized natural surface trails that are optimized for hiking and foot traffic but designed to accommodate multiple user groups | Steering Committee, Richmond Trails | Short-Term | Richmond Mountain Trails, VYCC | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New mountain bike trails | Build "bike-optimized" multi-use natural surface trails to ensure desired experiences for all user groups | Steering Committee, Richmond Trails | Medium-Term | Richmond Mountain Trails, Fellowship of the Wheel, VYCC | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New ADA accessible path | Explore opportunities for an accessible path for all ages and abilities to enjoy the forest. Topography may be a challenge. Such paths are typically short (~1 mile) and provide ample opportunities for rest and education with stations or stops next to points of natural or cultural interest. Coordinate with educational programming. | Steering Committee, Richmond Trails | Long-Term | Richmond Mountain Trails, VYCC | Trail design | $$$ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New backcountry/glade skiing opportunities | Explore opportunities for expanding backcountry/glade skiing in combination with sustainable forest management activities. | Steering Committee | Long-Term | County Forester, Richmond Mountain Trails, local skiers | Trail design | $$ | RTP, LF
Groom trails for cross-country skiing and fat biking | Groom wider trails for public cross-country skiing and fat biking. | Steering Committee, Richmond Trails | Long-Term | Richmond Mountain Trails, local skiers | -- | $$ | RTP
Trail markers and signage | Add signage in the forest for wayfinding, information, and trail etiquette. Ensure it communicates town ownership and/or steering committee management. | Steering Committee | Short-Term | Richmond Trails, VYCC, Richmond Mountain Trails, Conservation Commission | Signage design | $$ | RTP, RTC
Partner with local trails groups | Partner with Richmond Trails, Richmond Mountain Trails, and others to develop a trail system that fits the existing opportunities in Richmond and for volunteers for trail building and maintenance. | Steering Committee | Short-Term | Richmond Mountain Trails, Richmond Trails, Fellowship of the Wheel | -- | $ | RTP, NPCB
3. Other Facilities and Structures
Outdoor Classrom/Learning Lab | Create a small gathering space with log benches, earthen mounds etc. for schools and other groups. Coordinate needs with educational partners (RES, CHMS, MMU, UVM) | Steering Committee | Medium-Term | Program and educational partners | outdoor classroom design | $$ | LWCF, RTC, RTP, RFG, AIG
Pause Places | Develop a series of "Pause Places" along the trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, sunsets, rest, and rejuvenation. Opportunities for natural and historical interpretation should also be explored. Larger ones may include a picnic table. Some could also include public art or a 'little free library.' | Steering Committee | Medium-Term | Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Create and maintain locations for birding and viewing wildlife. | Build more locations to sit and observe wildlife. Benches are encouraged in a variety of locations. Coordinate with Pause Places. | Steering Committee | Medium-Term | Program and educational partners | Natural resource research, pause place design | $ | LWCF, RTC, RTP, RFG, AIG
Restroom facilities | Provide restroom facilities at the trailhead and/or outdoor classroom. | Steering Committee | Medium-Term | Public Works Department | Restroom design | $$ | LWCF, RD, VCDP, RFG, VCF, LF, AIG, BJF
Sledding | Utilize grazing pastures or other hilly slopes as designated sledding hill. | Steering Committee | Medium-Term | Recreation Committee | Design | $ | LWCF, RFG
Paddle/Watersports and swimming hole | Explore options in the broader community for paddle/watersports and a swimming hole. | Town | Long-Term | Recreation Committee | easements | $$ | LWCF, RD, RFG
Community Garden | Explore locations for accessible community garden or orchard. | Town | Long-Term | -- | -- | $$ | LWCF, RD, RFG
4. Education & Programs
Host school group programs in the forest | Bring students to the forest for ecology programs, recreation programs, etc. Consider a high school mountain biking team. | Program and educational partners | Medium-Term | Steering Committee | -- | $ | VCF, VHCB, LF, BJF
Kids Camps | Offer kids camps in the forest. Partner with Richmond Recreation Committee, churches and others operating camps in the area. | Progam and educational partners | Medium-Term | Steering Committee | -- | $ | VCF, VHCB, LF, BJF
Lessons, Skills Camps, and Clinics | Host lessons, skills camps, and clinics in the forest on mountain biking, trail running, or orienteering. Consider partnering with Richmond Mountain Trails, Richmond Trails, and Green Mountain Orienteering. | Progam and educational partners | Medium-Term | Steering Committee | -- | $ | VCF, VHCB, LF, BJF
Biodiversity Monitoring Program | Volunteer biodiversity monitoring program to study the affect of management on the forest. It could be part of research with a local higher education institution. | Steering Committee | Medium-Term | UVM, Conservation Commission |  | $ | VCF, VHCB, LF, BJF
Sustainable Forestry Demonstration Projects | Use the forest as a model and example of the value of healthy forests to the community, including promotion of educational demonstrations and tours. | Steering Committee | Medium-Term | County Forester |  | $ | VCF, VHCB, LF, BJF, CCG. ERG
Adult Ecology Programs | Host adult ecology programs (i.e., birding, plant identification) in the forest. | Steering Committee | Medium-Term | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Interpretive signage | Develop interpretive signage that support educational programs and self-guided learning. Coordinate with development of Pause Places | Steering Committee | Medium-Term | Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Species identification lists | Bird, plant and mammal species identification checklists could be developed and made available at the trailhead kiosk. Should also be utilized in education experiences. | Steering Committee | Medium-Term | Conservation Commission, Audubon | -- | $ | VCF, VHCB, LF, BJF
Story Walk | A Story Walk is an innovative and delightful way for children — and adults! — to enjoy reading and the outdoors at the same time. Laminated pages from a children's book are attached to wooden stakes, which are installed along an outdoor path. As you stroll down the trail, you're directed to the next page in the story. | Library | Medium-Term | Steering Committee | -- | $$ | VCF
5. Events
Races in the forest | Hold small-scale mountain bike or trail running races in the forest. Consider race series or local-serving adventure race (GMARA) as well . | Steering Committee | Medium-Term | Richmond Mountain Trails, Richmond Trails, GMARA | Event and parking plan | $ | VCF, VHCB, LF, BJF
6. Maps, Outreach, & Promotion
Develop and disseminate trail maps | Create maps that show all trails in the forest and make these maps readily available both online and in print. Explore opportunities to engage local businesses in sponsoring map printing. Ads from local businesses can not only fund map printing, but can also help connect forest use with economic activity in the region. | Steering Committee | Short-Term | Richmond Trails, VYCC, Richmond Mountain Trails, Conservation Commission | Graphic Design, Cartography | $-$$ | RTP
Town Forest Business Roundtable | Host a Town Forest Business Roundtable to share "trail friendly business" ideas that can help support trail use in the community, connect forest visitors with local businesses, and help support Town Forest efforts. | Steering Committee, Town | Long-Term | Local businesses, Lake Champlain Regional Chamber of Commerce | -- | $ | VCF
Leave No Trace | Include "Leave No Trace" messaging in maps, signage, social media, and other communications to encourage stewardship of resources, protect the user experience, and minimize the costs to the town for clean-up and restoration. | Steering Committee | Medium-Term | Conservation Commission | -- | $ | --
User group outreach | Hold dialogue programs with different groups with an educational focus. These programs should inform forest users about the ecological, recreational, educational, and agricultural values of the forest. | Steering Committee | Ongoing | All | -- | $ | RTP, NPCB
Hunter Engagement | Convene hunters to begin an on-going dialogue around hunting activities and to establish a framework for collaboration and coordination in the future. | Steering Committee | Ongoing | Local Hunters, Conservation Commission | -- | $ | NPCB
Richmond Trails Collaborative | Convene mountain bikers, hikers, and other user groups to begin an ongoing dialogue around trails and to establish a framework for collaboration in the future. Include both Richmond Trails and Richmond Mountain Trails and coordinate with trail system design and maintenance strategy. | Steering-Committee | Medium-Term | Richmond Trails, Richmond Mountain Trails, Richmond Rough Riders, Fellowship of the Wheel | Meeting facilitation | $ | RTP, NPCB
7. Administrative Actions
Adopt formal process for proposing and reviewing new trails and facilities | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. | Steering Committee | Short-Term | Conservation Commission, Town, VLT | Review, adjustment and adoption of model process | $ | RTP, RTC, VHCP, ERG
Management plan | Develop a forest management plan with provisions for partnerships and revisions. Plan should also have objectives to guide future management decisions. Consider management zones of the forest to consider and plan for all uses. Designate areas more suitable for wildlife habitat, hunting, or mountain biking, for example. | Steering Committee | Ongoing | Conservation Commission, Town, VLT | -- | $$ | CCG, MPG, ERG,VCF,VHCP,BJF
Cultural Resources studies | Conduct cultural resource studies to provide an improved understanding of human influences on the landscape. | Steering Committee | Ongoing | Conservation Commission, Town, VLT | -- | $$ | --
8. Partnerships
Partner with VYCC | Explore opportunities to partner with Vermont Youth Conservation Corps | Steering Committee | Ongoing | VYCC | -- | $ | --
Learn from other forests | Visit and meet with committees of other forests (i.e., Hinesburg) for ideas. | Steering Committee | Short-Term | Hinesburg and other nearby towns | -- | $ | --
Grazing | Work with Maple Wind Farm to continue grazing on existing pasture lands (possible revenue source for the forest). | Steering Committee | Medium-Term | Maple Wind Farm | Grazing Plan | $ | --
Agricultural use | Work with Maple Wind Farm to continue agricultural use on the property. Include agricultural education programs when possible. | Steering Committee | Medium-Term | Maple Wind Farm | Operations Plan | $ | --
Work with adjoining landowners | Work with adjoining landowners on access, connections, and management. | Steering Committee | Ongoing | Maple Wind Farm, VYCC, other adjacent landowners | -- | $ | --
9. Conservation and Natural Resources
Remove invasives | Develop a plan for managing non-native and invasive plants and work to remove invasive plants that are growing in the forest. | Steering Committee/ Conservation Commission | Medium-Term | VLT | -- | $ | ERG
Detailed habitat and natural resource surveys | Conduct detailed habitat and natural resource surveys to guide future management of the forest. Use these assessments to manage for future levels of use. | Steering Committee/ Conservation Commission | Ongoing | Conservation Commission, Vermont Land Trust | Detailed habitat and natural resource surveys | $$ | UVM, VHCP, LF, BJF, VCF
Wildlife Habitat | Protect critical wildlife habitat, including the heavily used deer wintering area (DWA) | Steering Committee/ Conservation Commission | Ongoing | VLT, UVM, neighbors, other natural resoruce partners | Detailed habitat and natural resource surveys | $$ | UVM, VHCP, LF, BJF, VCF
Support Biodiversity | Protect the uncommon Dry Oak Forest to benefit statewide biodiversity | Steering Committee/ Conservation Commission | Ongoing | VLT, UVM, neighbors, other natural resoruce partners | Detailed habitat and natural resource surveys | $$ | UVM, VHCP, LF, BJF, VCF
Wildlife Corridors | Maintain state significant corridor connections between and alongside Camel’s Hump State Park and Mt. Mansfield State Forest | Steering Committee/ Conservation Commission | Ongoing | VLT, UVM, neighbors, other natural resoruce partners | Detailed habitat and natural resource surveys | $$ | UVM, VHCP, LF, BJF, VCF
Forest Blocks | Conserve contiguous forestland (riparian zones) around significant surface water resources including vernal pools, streams, and wetlands to protect water quality and aquatic habitat. | Steering Committee/ Conservation Commission | Ongoing | VLT, UVM, neighbors, other natural resoruce partners | Detailed habitat and natural resource surveys | $$ | UVM, VHCP, LF, BJF, VCF
Forestry Management | Manage the forest to encourage a diversity of species and age classes which will result in resiliency. Plan for periodic timber harvesting to maintain working landscape and support the maintenance of healthy, intact ecosystem. Practice whole system approach that includes management for wildlife habitat. | Steering Committee/ Conservation Commission | Medium-Term | VLT, UVM, County Forrester | Forest Management Plan | $ | UVM, VHCP, LF, BJF, VCF

## Weathersfield
Strategy or Action | Description | Responsibility | Timing (Ongoing, short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Improve access to Town Forest Parcel | Increase the access to the Weathersfield Town Forest parcel by working with remaining land owners to open a new right of way to the town parcel. | Town | Ongoing | Private Landowners, FPR, AOT | Trail easements, AOT and FHWA Trail Proposal approval, NEPA Categorical Exclusion (CE; using the "Trail Construction and Reconstruction" exclusion) | $-$$$$ | LWCF, RTC, RTP, PBCG, RWJF, TCPN
Create designated parking area | Build a parking lot with a trailhead. Consider site on Thrasher Rd. closer to Weathersfield Town Forest. Municipal parking and access is preferred to using access through State Park. Ensure trailer space for equestrian use. Include park features such as informal field, bandstand, etc. | Town Forest Steering Committee/ Conservation Commission | Short-Term | Private Landowners | Parking lot design | $$$ | LWCF, RTP, RTC, RFG, TCPN
Vehicle wayfinding signage | Add vehicle wayfinding signage from villages and major roadways to the forest. | Town | Short-Term | Vtrans, Town Highway Department | Signage design | $$ | BPP, Vtrans Signage Program
Encourage linking trail networks to Village Center | Encourage the connectivity of trail networks with the Village Center and create access points and parking where trail users can depart or return to | Town | Medium-Term/Long-Term | Trails Collaborative | Trails Master Plan (not required, but helps) | $$$ | BCP, BPP
2. Trails
Existing trail conditions assessment and review | Study the trails and logging roads that currently exist on the property and consider potential for future trail building. Existing corridors may provide opportunities, but should be rebuilt to sustainable trail standards for both user experience and natural resource protection. | Town Forest Steering Committee/ Conservation Commission | Short-Term | Trails Collaborative, UVTA, ATA, STAB, GMHA, local builder/users | Trail reroute and redesign | $ | RTP, RTC, VHCP, ERG
Expand trail connectivity to other networks | Pursue avenues to connect Weathersfield trails to the current trail system on Mt. Ascutney. Connect to the Trail Around Mt. Ascutney. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Trails Collaborative, UVTA, ATA, STAB, GMHA, local builder/users | Regional Trails/Outdoor Recreation Master Plan | $$$ | RTP, RTC, RD, TAP, BPP, VCDP, RFG, VCF, BCP, MPG, LF, PBCG, AIG, RWJF, TCPN
New rugged multi-use trails | Develop multi-use non-motorized natural surface trails that are optimized for hiking and foot traffic but designed to accommodate multiple user groups | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Trails Collaborative, UVTA, ATA, STAB, GMHA, local builder/users | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New mountain bike trails | Build "bike-optimized" multi-use natural surface trails to ensure desired experiences for all user groups | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Trails Collaborative, UVTA, ATA, STAB, local builder/users | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
Plan trail system for equestrian use | Ensure multi-use non-motorized natural surface trails can accommodate equestrian and other uses. Develop equestrian-specific trails or spurs where necessary. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Trails Collaborative, Green Mountain Horse Association | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
New backcountry/glade skiing opportunities | Explore opportunities for expanding backcountry/glade skiing in combination with sustainable forest management activities. | Town Forest Steering Committee/ Conservation Commission | Long-Term | Trails, Collaborative, Catamount Trail Association | Trail design | $$ | RTP, LF
Groom trails for cross-country skiing and fat biking | Groom wider trails for public cross-country skiing and fat biking. | Trails Collaborative | Medium-Term | Ascutney Outdoors, STAB, ATA, UVTA | __ | $$ | RTP
Trail markers and signage | Add signage in the forest for wayfinding, information, and trail etiquette. Ensure it communicates town ownership and/or conservation commission management. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Trails, Collaborative, Ascutney Outdoors, STAB, ATA, UVTA, GMHA | Signage design | $$ | RTP, RTC
Partner with local trails groups to form a Trails Collaborative | Partner with Ascutney Trails Association, Sports Trails of Ascutney Basin, and others to form a Trails Collaborative and develop a trail system that fits the existing opportunities in Weathersfield region and for volunteers for trail building and maintenance. | Trails Collaborative | Short-Term | Ascutney Outdoors, STAB, ATA, UVTA, GMHA | Meeting facilitation | $ | NPCB
Regional trail connections | Explore opportunities for connections to trails in other sections of Weathersfield and nearby NH. Possible trails include the Sugar River Trail, Crown Military Road, and the North Springfield Lake Trails. | Trails Collaborative | Medium/ Long-Term | UVTA, ATA, STAB, GMHA local builder/users | Regional Trails/Outdoor Recreation Master Plan | $$$$ | RTP, RD, TAP, BPP, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
3. Other Facilities and Structures
Cabin/Hunting Camp Improvement | Explore opportunities to improve the cabin to better support day use, educational use, and potentially overnight use. Explore a relationship with Vermont Huts Association. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Vermont Huts Association, program and educational partners | Potentially architectural depending on level of improvement | $$$-$$$$ | LWCF, RTC, RTP, RFG, AIG
Pause Places | Develop a series of "Pause Places" along the trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, sunsets, rest, and rejuvenation. Opportunities for natural and historical interpretation should also be explored. Larger ones may include a picnic table. Some could also include public art or a 'little free library.' | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Trails Collaborative, Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Create and maintain locations for birding and viewing wildlife. | Build more locations to sit and observe wildlife. Benches are encouraged in a variety of locations. Coordinate with Pause Places. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Program and educational partners | Natural resource research, pause place design | $ | LWCF, RTC, RTP, RFG, AIG
4. Education & Programs
Host school group programs in the forest | Bring students to the forest for ecology programs, recreation programs, etc. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Weathersfield School and other program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Lessons, skills camps, and clinics | Offer lessons, skills camps, and clinics for trail running and mountain biking. | Program and educational partnerships | Medium-Term | STAB, Ascutney Outdoors, Paradise Sports, Vermont Youth Cycling, Windsor Bike Club | -- | $ | VCF, VHCB, LF, BJF
Ecology tours | Offer ecology tours (birdwatching, plant identification, etc.) for children and adults. | Program and educational partnerships | Medium-Term | Town and forest steering committee | -- | $ | VCF, VHCB, LF, BJF
Education Programs | Host educational programs in the forest about ecology and the arts such as nature photography or wildlife sketching programs. Explore partnership with the Library and other local groups. | Program and educational partnerships | Medium-Term | Town and forest steering committee | -- | $ | VCF, VHCB, LF, BJF
Story Walk | A StoryWalk is an innovative and delightful way for children — and adults! — to enjoy reading and the outdoors at the same time. Laminated pages from a children's book are attached to wooden stakes, which are installed along an outdoor path. As you stroll down the trail, you're directed to the next page in the story. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Proctor Library | -- | $$ | VCF
Species identification lists | Bird, plant and mammal species identification checklists could be developed and made available at the trailhead kiosk. Should also be utilized in education experiences. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Program and educational partners | -- | $ | VCF, VHCB, LF, BJF
Valley Quest | Participate in the Valley Quest with an offering in the Town Forest, potentially connected to the cabin site. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Valley Quest | -- | $ | VCF
Interpretive signage | Develop interpretive signage that support educational programs and self-guided learning. Coordinate with development of Pause Places | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Program and educational partners | Historical and natural resource research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
5. Events
Races in the forest | Hold small-scale race events (running, XC skiing, mountain biking, etc.) or local-serving adventure race (Tough Mudder, Warrior Dash, etc.) in the forest and/or around Mt. Ascutney. | Race and Event Partners | Medium-Term | Ascutney Outdoors, STAB, ATA, UVTA, Windsor Bike Club | event and parking plan | $ | VCF, LF, BJF
Equestrian Events | Identify means to host and promote equestrian events in the forest. Consider coordinating with Green Mountain Horse Association. | Race and Event Partners | Medium-Term | Green Mountain Horse Association, Ascutney Outdoors | event and parking plan | $ | VCF, LF, BJF
Competitive trail riding and endurance races | The campground at Ascutney State Park could service riders for a larger biking race in the forest. This type of ride center could lead to IMBA qualification. | Race and Event Partners | Medium-Term | STAB, ATA, Ascutney Outdoors, Windsor Bike Club | event and parking plan | $ | VCF, LF, BJF
Recreational Events | Hold community-oriented recreational events such as a moonlight snowshoe hike in the Town Forest. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | Ascutney Outdoors, Town | event and parking plan | $ | VCF, LF, BJF
6. Maps, Outreach, & Promotion
Develop and disseminate trail maps | Create maps that show all trails in the forest and make these maps readily available both online and in print. Consider opportunities to integrate with regional mapping efforts and Upper Valley Trails Alliance (UVTA). Explore opportunities to engage local businesses in sponsoring map printing. Ads from local businesses can not only fund map printing, but can also help connect forest use with economic activity in the region. | Town Forest Steering Committee/ Conservation Commission | Short-Term | Trails Collaborative, STAB, Ascutney Outdoors, Paradise Sports, Windsor Bike Club, UVTA, Chamber of Commerce | Graphic design, cartography | $-$$ | RTP
Building a coalition of volunteers | Have a group of volunteers on hand for activities such as trail maintenance, events or other needs of the forest. Look to engage the Ascutney Trails Association, Weathersfield Pathfinders, Sports Trails of Ascutney Basin, Springfield High School/Hartford/Claremont VOTEC. | Trails Collaborative | Ongoing | Ascutney Trails Association, Weathersfield Pathfinders, Sports Trails of Ascutney Basin, Springfield High School/Hartford/Claremont VOTEC., UVLT | -- | $ | NPCB
Outdoor Recreation Business Roundtable | Host an Outdoor Recreation Business Roundtable to share "trail friendly business" ideas that can help support trail use in the community, connect forest visitors with local businesses, and help support Town Forest efforts. | Town Forest Steering Committee/ Conservation Commission | Long-Term | Chamber of Commerce, local businesses | -- | $ | VCF
Online presence | Improve the online presence of the forest with a forest specific website. Work with Chamber of Commerce and UVTA to coordinate activities to promote the forest. | Town Forest Steering Committee/ Conservation Commission | Short-Term | Chamber of Commerce, UVTA, Ascutney Outdoors | Website design | $-$$ | RTP, VCF
7. Administrative Actions
Management plan | Develop a forest management plan for the long term success of the forest. Ensure it includes provisions for partnerships and revisions. Coordinate with management zones in the forest. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | UVLT | __ | $$ | CCG, MPG, ERG, VCF, VHCP, BJF
Management zones | Consider management zones of the forest to consider and plan for all uses. Designate areas more suitable for wildlife habitat, hunting, or mountain biking, for example. | Town Forest Steering Committee/ Conservation Commission | Medium-Term | UVLT | Management Plan | $ | CCG, MPG, ERG, VCF, VHCP, BJF
Adopt formal process for proposing and reviewing new trails and facilities | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. | Town Forest Steering Committee/ Conservation Commission | Short-Term | UVLT | Review, adjustment and adoption of model process | $ | --
Work with Upper Valley Land Trust | As the Town Forest is under a conservation easement held by the UVLT, the town must work with UVLT on future projects to ensure that they abide by the terms of the easement. Also engage UVLT for technical assistance and volunteer recruitment. | Town Forest Steering Committee/ Conservation Commission | Short-Term | UVLT | -- | $ | --

## Woodbury
Strategy or Action | Description | Responsibility | Timing (Ongoing, short, medium, and long-term) | Partners Involved | Planning required | Relative Cost ($-$$-$$$-$$$$) | Funding Opportunities
1. Parking & Access
Parking lot and trailhead development | Develop a parking lot along Town Farm Road with a trailhead kiosk.. | Conservation Commission | Short=Term | Town | Parking lot design | $$$$ | LWCF, RTP, RTC, TAP, RFG
Access paths and connections | Develop access path between the town forest trailhead and the Woodbury Elementary/Post Office area. | Conservation Commission/Town | Long-Term | School District | Scoping study/trail plan | $$-$$$ | BCP, BPP, STBG, TAP, MPG
Vehicle wayfinding signage | Add vehicle wayfinding signage from town and major roadways to the forest. | Town | Medium-Term | Vtrans | Signage design | $$ | Vtrans Signage Program, BPP
Forest kiosk | Place forest kiosk with maps and wayfinding signage at the Post Office. | Conservation Commission | Medium=Term | Town, Post Office | Kiosk design, mapping | $ | RTP, RTC, AIG
2. Trails
Existing trail conditions assessment and review | Study the trails and logging roads that currently exist on the property and consider potential for future trail building. Existing corridors may provide opportunities, but should be rebuilt to sustainable trail standards for both user experience and natural resource protection. | Conservation Commission | Short=Term | VYCC, local trail builders/users | Trail reroute & design | $ | RTP, RTC, VHCP, ERG
New rugged multi-use paths | Develop rugged, multi-use, non-motorized paths that are designed to accommodate multiple user groups (i.e., hikers, snowshoers, dogwalkers) | Conservation Commission | Short=Term | VYCC, local trail builders | Trail design | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
Trail markers and signage | Add signage in the forest for wayfinding, information, and trail etiquette. Ensure it communicates town ownership and/or conservation commission management. | Conservation Commission | Short=Term | VYCC | Signage design | $$ | RTP, RTC
Nature Interpretation Trail | Develop a nature trail loop with interpretive signage about the forest. | Conservation Commission | Medium=Term | VYCC | Trail design, natural resource research, pause places | $$ | RTP, RD, VCDP, RFG, VCF, LF, PBCG, RWJF, TCPN
Partner with VYCC on trail building | Continue working with VYCC on trail design, building, and maintenance strategies. | Conservation Commission | Ongoing | VYCC | -- | $$ | --
Convene local trails group | Partner with local trail supporters for volunteers for trail building and maintenance. | Conservation Commission | Short=Term | Local trail users | Meeting facilitation | $ | NPCB
3. Other Facilities and Structures
Outdoor Classroom/Learning Lab | Create a small gather space with log benches, earthen mounds etc. for schools and other groups at the Town Wetland parcel. . | Woodbury Elementary School, Friends of Woodbury Elementary School | Short=Term | Conservation Commission, Four Winds | Classroom/Playground./Viewing Pier Design | $$ | LWCF, RTC, RTP, RFG, AIG
Pause Places | Develop a series of "Pause Places" along the trail system. These may be a rest stop, an informational stop, or both. All pause places should include a bench or appropriate rocks/boulders for seating and should capitalize on locations with the potential for views, sunsets, rest, and rejuvenation. Opportunities for natural and historical interpretation should also be explored. Larger ones may include a picnic table. Some could also include public art or a 'little free library.' | Conservation Commission | Medium-Term | Program and educational partners | Historical and natural resources research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Wildplay or natural playground at Town Wetland | Natural playgrounds are play environments that blend natural materials, features, and indigenous vegetation with creative landforms to teach children about the wonders and intricacies of the natural world while they play within it. | Woodbury Elementary School, Friends of Woodbury Elementary School | Medium-Term | Conservation Commission | Classroom/Playground./Viewing Pier Design | $$ | LWCF, RD, RFG
Educational viewing pier | Add an educational viewing pier at the edge of the wetland for classes to gather. Boardwalk and bridges may also be necessary at wet spots on trails near the wetland. | Woodbury Elementary School, Friends of Woodbury Elementary School | Medium-Term | Conservation Commission, Four Winds | Classroom/Playground./Viewing Pier Design | $$ | LWCF, RTC, RTP, RFG, AIG
4. Education & Programs
Partnerships with local schools | Host frequent field trips about ecology and local history in the forest and wetland. Seek regional school partnerships as well. | Conservation Commission | Ongoing | Woodbury Elementary School, Friends of Woodbury Elementary School, Four Winds, other local schools | -- | $ | --
Partnerships with state/local groups, camps, etc. | Host kids camp, retreats, or educational activities in the forest. | Conservation Commission | Medium-Term | Four Winds, day camps, and other program and educational partners | -- | $ | --
Education Programs | Host educational programs in the forest about ecology and the arts such as nature photography or wildlife sketching programs. | Program and educational partners | Medium-Term | Four Winds, Conservation Commission | -- | $ | VCF, VHCB, LF, BJF
Ecology tours | Offer ecology tours (birdwatching, plant identification, etc.) for children and adults. | Program and educational partners | Short-Term | Four Winds, Conservation Commission | Ecological research | $ | VCF, VHCB, LF, BJF
Interpretive signage | Develop interpretive signage that support educational programs and self-guided learning. Coordinate with development of pause places | Conservation Commission | Medium-Term | Four Winds, Woodbury Elementary School | Historical and natural resources research, pause place design | $$ | LWCF, RTC, RTP, RFG, AIG
Story Walk | A StoryWalk is an innovative and delightful way for children — and adults! — to enjoy reading and the outdoors at the same time. Laminated pages from a children's book are attached to wooden stakes, which are installed along an outdoor path. As you stroll down the trail, you're directed to the next page in the story. | Conservation Commission | Short-Term | Library | -- | $$ | --
Species identification lists | Bird, plant and mammal species identification checklists could be developed and made available at the trailhead kiosk. Should also be utilized in education experiences. | Conservation Commission | Short-Term | Program and educational partners, Four Winds, Harwick Trails | Ecological research | $ | VCF, VHCB, LF, BJF
5. Maps, Outreach, & Promotion
Develop and disseminate trail maps | Develop trail maps and print and post at the trailhead and at the post office. Also post the trail map online on a town forest website. | Conservation Commission | Medium-Term | -- | Graphic design, Cartography | $$ | RTP
Promote forest and wetland to nearby towns | Invite nearby schools to participate in outdoor education programming at the wetland and forest. | Conservation Commission | Medium-Term | Orleans Southwest Supervisory Union, Four Winds | -- | $ | --
Learn from other forests and outdoor education programs. | Meet with committees of other forests (i.e., Hardwick) for ideas about nature-based education. | Conservation Commission | Short-Term | Hardwick Trails | -- | $ | --
6. Administrative Actions
Management plan | Develop a forest management plan for the long term success of the forest. Ensure it includes provisions for partnerships and revisions. Coordinate with management zones in the forest. | Conservation Commission | Medium-Term | Town, forest users and volunteers | Management Plan | $$ | CCG, MPG, ERG, VCF, VHCP, BJF
Management zones | Consider management zones of the forest to consider and plan for all uses. Designate areas more suitable for wildlife habitat, hunting, or hiking, for example. | Conservation Commission | Medium-Term | Town, forest users and volunteers | Management Plan | $ | CCG, MPG, ERG, VCF, VHCP, BJF
Adopt formal process for proposing and reviewing new trails and facilities | Process will include ecological concerns and will provide all stakeholders and user groups an opportunity to propose new trails and facilities. | Conservation Commission | Short-Term | Town, forest users and volunteers | Review, adjustment, and adoption of model process | $ | RTP, RTC, VHCP, ERG
Work with adjoining landowners | Work with adjoining landowners on access, connections, and management. | Conservation Commission | Ongoing | Neighbors | -- | $ | --

## Funding Key
Funding Sources
B - Bonds | NNI - Sireea Club's Nearby Nature Initiative
BHG - Bell Helmut Built Grants | PDFR - Private Doners & Fund Raising
BPP - VTrans Bicycle and Pedestrian Program | PBCF - People for Bikes Community Fund
BRP - Vtrans Better Roads Program | RD - USDA Rural Development Grant Assistant
CCG - ANR Caring for Canopy Grant Program | REDG - BGS Regional Economic Development Grant Program
CDBG - ACCD Vermont Community Development Program | RFG - Recreational Facilities Grants
CFG - Cultural Facilities Grant Program | RTC - NPS Rivers, Trails, & Conservation Assistasnce Program
DIF - Development Impact Fees | RTP - ANR Recreation Trails Grant Program
EGR - ANR Eccosystem Restoration Grant Program | RWJF - Robert Wood Johnson Foundation Grants
FLAP - Federal Land Access Program | SIB - State Infrastructure Bank Grant or Loan
HSG - VTrans Highway Safety Grants | STP - Vtrans Surface Transportation Program
LF - Local Funds | STPG - Vtrans Surface Transportation Program Signage
LWCF - ANR Land and Water Conservation Fund | TAP - VTrans Transportation Alternatives Program
MMPG -Municipal Mitigation Program Grant | THC2SG - Class 2 Town Highway and Structures Grants
MPG - ACCD Municipal Planning Grant | TPI - Transportation Planning Initiative